## Team_Info
Name | Abbr | Nokia ID | Email Address
Zhou, Changping | ZCP | 69005657 | changping.zhou@nokia-sbell.com
Ren, Liyue | RLY |  | liyue.ren@nokia-sbell.com
Xu, Mi 1 | XM | 62157104 | mi.1.xu@nokia-sbell.com
Yuan, Jia 1 | YJ |  | jia.1.yuan@nokia-sbell.com
Song, Yongju | SYJ |  | yongju.song@nokia-sbell.com
Chan, Kavin | CK |  | kavin.chan@nokia-sbell.com
Tian, Lihua | TLH |  | lihua.tian@nokia-sbell.com

## Team_Work_Info
Name | Abrr | Nokia Id | email | FB1805 |  | FB1806 |  | FB1807 |  | FB1808 |  | FB1809 |  | FB1810
|  |  |  | AL(day) | FB1805 effert(h) | AL(day) | FB1806 effert(h) | AL(day) | FB1807 effert(h) | AL(day) | FB1808 effert(h) | AL(day) | FB1809 effert(h) | AL(day) | FB1810 effert(h)
Zhou, Changping | ZCP | 69005657 | changping.zhou@nokia-sbell.com | 0 | 78 | 5 | 0 | 0 | 0 | 0 | 0
Ren, Liyue | RLY |  | liyue.ren@nokia-sbell.com | 0 | 90 | 2 | 0 | 0 | 0 | 0 | 0
Xu, Mi 1 | XM | 62157104 | mi.1.xu@nokia-sbell.com | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
Yuan, Jia 1 | YJ |  | jia.1.yuan@nokia-sbell.com | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0
Song, Yongju | SYJ |  | yongju.song@nokia-sbell.com | 0 | 146 | 0 | 0 | 0 | 0 | 0 | 0
Chan, Kavin | CK |  | kavin.chan@nokia-sbell.com | 0 | 130 | 2 | 0 | 0 | 0 | 0 | 0
Tian, Lihua | TLH |  | lihua.tian@nokia-sbell.com | 0 | 102 | 3 | 0 | 0 | 0 | 0 | 0

## FB1805_Plans
Module | Task | Priority | Owner | EE
Download | Detail design for download procedure in controller |  | YJ | 12
| Detail design for Cancellation request in download procedure in controller |  | ZCP | 12
| Migration difference from sbts16 to current branch |  | YJ | 12
| Code & UT for download procedure in controller |  | YJ | 18
| Code & UT for Cancellation procedure in controller |  | ZCP | 12
| Review from TL & Arch for Download/Cancelation ACC |  | YJ | 12
Progress and error update
| Detail design progress update for Download procedure of error and common process in controller |  | CK | 12
| Code & UT for progress update of Download procedure of error/common process |  | CK | 12
| Detail design for progress update of (A/P/C/R) procedure of error process in in controller |  | CK | 6
| Detail design for progress update of (A/P/C/R) procedure of common process in controller |  | CK | 6
| Code & UT for (A/P/C/R) progress update for netAct SWM of common process |  | CK | 12
| Code & UT for (A/P/C/R) progress update for netAct SWM of error process |  | CK | 12
| Code & UT for parseNetActRaml function |  | CK | 6
| Migration difference from sbts16 to current branch |  | CK | 12
Design for Rollback | Design for Rollback |  | CK
Provision
| Detail design for Provision procedure in controller |  | TLH | 12
| Detail design for Cancellation request in Provision procedure in controller |  | TLH | 12
| Code & UT for Provision procedure in controller |  | TLH | 12
| Code & UT for Cancellation procedure in controller |  | TLH | 12
| Migration difference from sbts16 to current branch |  | TLH | 12
| Code & UT for active request for (D/A/P/C/R) in planChecker |  | TLH | 12
| Review from TL & Arch for Provision/Cancelation ACC |  | TLH | 12
PreHandle all swm requests
| Code & UT for Download procedure in eventHandler |  | SYJ | 8
| Code & UT for Download procedure in planchecker |  | SYJ | 8
| Design for eventHandle (A/P/C/R) request from netAct to controller |  | SYJ | 12
| Design for plan (D/A/P/C/R) request from netAct to controller |  | SYJ | 12
| Code & UT for initialize of swm event handler |  | SYJ | 12
| Code & UT for handle swm plan change events |  | SYJ | 18
| Code & UT for exception in eventHandler |  | SYJ | 12
| Migration difference from sbts16 to current branch |  | SYJ | 12
Activation
| Detail design for Activation procedure in controller |  | RLY | 18
| Code & UT for start Activation request in controller |  | RLY | 12
| Migration difference from sbts16 to current branch |  | RLY | 12
| Detail design for Rollback procedure in controller |  | RLY | 18
| Review from TL & Arch for Activation ACC |  | RLY | 12
Validation for all swm requests
| Code & UT for planChecker Download of validation for netAct request |  | ZCP | 10
| Code & UT for planChecker Provision of validation for netAct request |  | YJ | 12
| Code & UT for planChecker Activation of validation for netAct request |  | ZCP | 8
| Code & UT for planChecker Cancellation of validation for netAct request |  | ZCP | 10
| Code & UT for planChecker Rollback of validation for netAct request |  | YJ | 12
| Migration difference from sbts16 to current branch D/A/P/C/R |  | ZCP | 8
Merge request |  |  | ALL | 12
Demo for function |  |  | ALL | 6
Rollback | Migration difference Rollback plan from sbts16 to current branch |  | SYJ | 6
| Design for plan rollback request from netAct to controller |  | SYJ | 6
| Code & UT for rollback procedure in eventHandler and plan |  | SYJ | 18
| Migration difference Rollback controller from sbts16 to current branch |  | YJ | 6
| Design for rollback controller |  | YJ | 6
| Code & UT for rollback procedure in controller |  | YJ | 18
| Migration difference Rollback status from sbts16 to current branch |  | CK | 6
| Design for rollback Rollback status |  | CK | 6
| Code & UT for rollback status |  | CK | 18
| Merge request of rollback planchecker |  | SYJ | 4
| Merge request of rollback rollback status |  | CK | 4
| Merge request of rollback rollback controller |  | YJ | 4
Review from TL & Arch of Rollback design
Code & UT for start Rollback request in controller
Design for (D/A/P/C/R) accroding to detail design after EFS coming
backlog | Design for Provision/Cancellation accroding to detail design after EFS coming
Design for D/P/A/C/R accroding to detail design after EFS coming
design for progress update for (D/A/P/C/R) accroding to detail design after EFS coming
Design for Download/Cancellation accroding to detail design after EFS coming
Design for Activation accroding to detail design after EFS coming
Can be change the roles
Preparation for next FB | Provision
draft design
design can be team review
design review by TL
design review by Arch
Cancellation
Rollback
SCT for provision/rollback/cancel
说明 | 紫色为第一优先级完成。

## FB1806_Plans
Module | Task | Priority | Owner | EE
Download
Progress and error update
Provision
PreHandle all swm requests
Activation
Validation for all swm requests
Validation for all swm requests
Validation for all swm requests
Merge request |  |  |  | 0
Demo for function |  |  |  | 0

## FB1807_Plans
Module | Task | Priority | Owner | EE
Download
Progress and error update
Provision
PreHandle all swm requests
Activation
Validation for all swm requests
Validation for all swm requests
Validation for all swm requests
Merge request |  |  |  | 0
Demo for function |  |  |  | 0

## FB1808_Plans
Module | Task | Priority | Owner | EE
Download
Progress and error update
Provision
PreHandle all swm requests
Activation
Validation for all swm requests
Validation for all swm requests
Validation for all swm requests
Merge request |  |  |  | 0
Demo for function |  |  |  | 0

## Sheet4
Download
Progress and error update
Provision
PreHandle all swm requests
Activation
Validation for all swm requests
Validation for all swm requests
Validation for all swm requests
Merge request | ALL | 12
Demo for function | ALL | 6